## Tracker
PROJECT TRACKER
CATEGORY | ACTION | STATUS | PRIORITY | HOURS | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
US-01 ¦ As a user, I want to be able to see a dynamic UI that is updated after each message I send rather than a conversational back-and-forth with UI components. |  |  |  | 5 | 2026-04-08 | 2026-04-08 | 1 |  | Total for Week | 11
↳ Task | Remove UI Components from convo output (keep final summary) | Complete | Medium | 1 | 2026-04-08 | 2026-04-08 | 1
↳ Task | Move UI Drawer components into main area of UI | Complete | Medium | 2 | 2026-04-08 | 2026-04-08 | 1
↳ Task | Move current chat (user query, llm final summary) to floating window | Complete | Medium | 2 | 2026-04-08 | 2026-04-08 | 1
US-02 ¦ As a user, I need to be able to see live/real-time data being streamed from backend to UI components. |  |  |  | 14 | 2026-04-08 | 2026-04-13 | 6
↳ Task | Research whether to send live updates like this MCP -> Orchestrator -> UI or MCP -> UI | Complete | High | 1 | 2026-04-08 | 2026-04-08 | 1 | MCP -> Orchestrator -> UI
↳ Task | Implement live stream using websockets | Complete | High | 8 | 2026-04-08 | 2026-04-09 | 2
↳ Task | Test accuracy and performance | Complete | Low | 5 | 2026-04-09 | 2026-04-13 | 5
US-03 ¦ As a user, I want to be able to use this system on Desktop, Browser, Tablet, Mobile, Watch, and TV. |  |  |  | 31
↳ Task | Convert React frontend to Flutter | Ready to Start | Low | 21
↳ Task | Connect Watch + TV to mobile device related to user (QR code shown on screen, scanned by mobile) | Ready to Start | Low | 8
↳ Task | Notification preferences | Ready to Start | Low | 2
US-04 ¦ As a user, I need to be able to see the audit log of agent actions. |  |  |  | 6 | 2026-04-28 | 2026-04-28 | 1
↳ Task | Add button and container to bring up audit log. | Complete | High | 1 | 2026-04-28 | 2026-04-28 | 1
↳ Task | Save all agent actions in database. | Complete | High | 2 | 2026-04-28 | 2026-04-28 | 1
↳ Task | Connect frontend to backend to display agent audits. | Complete | High | 3 | 2026-04-28 | 2026-04-28 | 1
US-05 ¦ As a user, I need to be able to upload a variety of file types. |  |  |  | 11 | 2026-04-13 | 2026-04-17 | 5
↳ Task | Add support for "normal" file type uploads (png, jpeg, md, csv, etc) | Complete | Medium | 2 | 2026-04-13 | 2026-04-13 | 1
↳ Task | Test normal file upload | Complete | Medium | 2 | 2026-04-13 | 2026-04-13 | 1
↳ Task | Add support for medical specific file type uploads (dicom, nzi, czi, etc) | Complete | Medium | 2 | 2026-04-17 | 2026-04-17 | 1
↳ Task | Create tools to read these files and return data. | Complete | Medium | 5 | 2026-04-17 | 2026-04-17 | 1
US-06 ¦ As a user, I want to be able to provide feedback on the output of components. As a developer, I want the system to take this feedback and auto update tools that continue to produce errors. |  |  |  | 10 | 2026-04-28 | 2026-05-01 | 4
↳ Task | Add thumbs up/down -> if thumbs down then show modal for feedback. | Complete | Low | 1 | 2026-04-28 | 2026-04-28 | 1
↳ Task | Use the secondary LLM to read feedback and propose changes (every day), possibly create a PR for review. | Complete | Low | 1 | 2026-04-28 | 2026-04-28 | 1
↳ Task | Create tools to read these files and return data. | Complete | Low | 8 | 2026-04-28 | 2026-04-28 | 1
US-07 ¦ As a developer, I need mock auth logic to test the system without having to actually log into the system. |  |  |  | 2 | 2026-04-13 | 2026-04-17 | 5
↳ Task | Reconnect VITE_MOCK_AUTH environment variable back to the system (or fix where its broken). | Complete | Medium | 2 | 2026-04-13 | 2026-04-17 | 5
US-08 ¦ As a user, I want tool tips and a getting started tutorial. |  |  |  | 6 | 2026-04-28 | 2026-04-28 | 1
↳ Task | Write a guide. | Complete | Low | 1 | 2026-04-28 | 2026-04-28 | 1
↳ Task | Add first user tutorial/walkthrough. | Complete | Low | 3 | 2026-04-28 | 2026-04-28 | 1
↳ Task | Warning about not HIPAA compliant. | Complete | Low | 1 | 2026-04-28 | 2026-04-28 | 1
↳ Task | Add it to the navbar as a link. | Complete | Low | 1 | 2026-04-28 | 2026-04-28 | 1
US-09 ¦ As a user, I want to use my own LLM subscription. |  |  |  | 4 | 2026-04-28 | 2026-04-28 | 1
↳ Task | Research if Astral can see the amount of tokens left. | Complete | Low | 1 | 2026-04-28 | 2026-04-28 | 1 | Can't see if you are going to run out of tokens :(, but will add token usage to frontend.
↳ Task | Move LLM .env vars to frontend. | Complete | Low | 3 | 2026-04-28 | 2026-04-28 | 1
US-10 ¦ As a user, I want a condensed view of all the sidebar buttons. |  |  |  | 2 | 2026-04-30 | 2026-04-30 | 1
↳ Task | Add a settings/options/something button that shows all the new buttons (audit, tutorial,etc) | Complete | Medium | 2 | 2026-04-30 | 2026-04-30 | 1
US-11 ¦ As a user, I want the new chat button to be on the sidebar above recent chats. |  |  |  | 1 | 2026-05-06 | 2026-05-06 | 1
↳ Task | Move new chat button in navbar to sidebar only. | Complete | Low | 1 | 2026-05-06 | 2026-05-06 | 1
US-12 ¦ As a user, I want the screen not to flash on page load and when new UI components are being added to the screen. |  |  |  | 6 | 2026-05-01 | 2026-05-01 | 1
↳ Task | Investigate why this is happening. | Complete | High | 1 | 2026-05-01 | 2026-05-01 | 1
↳ Task | Implement fix. | Complete | High | 5 | 2026-05-01 | 2026-05-01 | 1
US-13 ¦ As a user, I want to be able to create and test a new agent through the UI. |  |  |  | 16 | 2026-05-01 | 2026-05-06 | 6
↳ Task | Fix the Agent creation flow to get to the agent test screen. | Complete | High | 3 | 2026-05-01 | 2026-05-03 | 3
↳ Task | Have the draft agent actually start running and responding to the user. | Complete | High | 3 | 2026-05-01 | 2026-05-03 | 3
↳ Task | Have the draft agent, on approval, get addded to the list of live agents. | Complete | High | 2 | 2026-05-01 | 2026-05-03 | 3
↳ Task | Make the agent the user created appear in my agents, not just public agents? | Complete | High | 3 | 2026-05-06 | 2026-05-06 | 1
↳ Task | Make it clear what agent is being used when I start a new chat or message | Complete | Medium | 2 | 2026-05-06 | 2026-05-06 | 1
↳ Task | The read writes etc that we turn on should be specific for each tool, make the 'i' pop-ups appear before the on button is switched on | Complete | Medium | 3 | 2026-05-06 | 2026-05-06 | 1
US-14 ¦ As a user, I want to select the tools I want to call with a query. |  |  |  | 8 | 2026-05-06 | 2026-05-06 | 1
↳ Task | Add option in chat to allow user to pick which tools they want to use. | Complete | Medium | 8 | 2026-05-06 | 2026-05-06 | 1
↳ Task | Test to make sure system still respects the scopes and only looks at selected tools for a query. | Complete | Medium | 3 | 2026-05-06 | 2026-05-06 | 1
US-15 ¦ As a user, I want to see progress notifications in the chat when my query is being processed. |  |  |  | 8 | 2026-05-06 | 2026-05-06 | 1
↳ Task | While waiting for tools to be aggregated, display messages like how claude does it: "sussing…, clauding…" etc. | Complete | Medium | 5 | 2026-05-06 | 2026-05-06 | 1
↳ Task | Output the steps that the system is taking. Instead of showing which tools are being called in the processing message, have those messages persist in the chat so a user can see what is being called. | Complete | Medium | 3 | 2026-05-06 | 2026-05-06 | 1
US-16 ¦ As a user, I want realtime voice in/out with the system. |  |  |  | 7
↳ Task | Investigate this openai article and see how they are doing it: https://openai.com/index/delivering-low-latency-voice-ai-at-scale/ | Ready to Start | Low | 2
↳ Task | Attempt to make the current voice in/out system based on the openai article to scale. | Ready to Start | Low | 5
US-17 ¦ As a user, I want a better tutorial that won't make me want to skip it as soon as I see it. |  |  |  | 9
↳ Task | Investigate this article and see how they are doing it: https://productonboarding.com/articles/why-product-tours-get-skipped | Ready to Start | Low | 2
↳ Task | Udpate the tutorial code to be less intrusive. | Ready to Start | Low | 5
↳ Task | Write better steps in the tutorial. | Ready to Start | Low | 2
US-18 ¦ As a user, I want a cohesive, unified generated UI instead of the components being sectioned off in their own components. |  |  |  | 8 | 2026-05-13
↳ Task | Remove the UI containers. | In Progress | Medium | 3 | 2026-05-13
↳ Task | Autocondense UI and make it scrollable. | In Progress | Medium | 5 | 2026-05-13
US-19 ¦ As a developer, I want to connect Classify, forecaster, and LLM factory as agents to this system. |  |  |  | 11 | 2026-05-07 | 2026-05-13 | 7
↳ Task | Create agent for Classify | Complete | High | 5 | 2026-05-07 | 2026-05-11 | 5
↳ Task | Create agent for Forecaster | Complete | High | 3 | 2026-05-07 | 2026-05-13 | 7
↳ Task | Create agent for LLM Factory | Complete | High | 3 | 2026-05-07 | 2026-05-13 | 7
US-20 ¦ As a user, I want submit queries and have them run asynchronously, so I can navigate away from the session and get a notification when it is finished. |  |  |  | 3
↳ Task | Implement asynchronous | Ready to Start | High | 3
US-21 ¦ As a user, I want the output ui components to be able to play sounds, if applicable. |  |  |  | 5
↳ Task | Use vaidens piano agent to test ui components that play sound. | Ready to Start | Low | 5
US-22 ¦ As a user, I want all the Claude agents/connectors :) |  |  |  | 0
↳ Task | Claude for Excel | Ready to Start | Low
↳ Task | Claude for PowerPoint | Ready to Start | Low
↳ Task | Claude for Word | Ready to Start | Low
↳ Task | Claude for Outlook | Ready to Start | Low
↳ Task | Claude for building pitch templates, conducting validation reviews | Ready to Start | Low
↳ Task | Claude Adaptive Runtime Intelligence | Ready to Start | Low
↳ Task | Claude blender (it like debugs or batch applies changes across objects) | Ready to Start | Low
↳ Task | Claude Adobe Creative Cloud | Ready to Start | Low
↳ Task | Claude Canva Affinity | Ready to Start | Low
↳ Task | Claude interactive artifacts/dadhboards | Ready to Start | Low
↳ Task | Claude design | Ready to Start | Low
↳ Task | an agent that will critique constituions in spec-driven dev | Ready to Start | Low
↳ Task | An agent that can like visual graph networks like obsidan does | Ready to Start | Low
↳ Task | Claude code review | Ready to Start | Low

## Summary
TIME & EFFORT SUMMARY DASHBOARD
Total Hours | Tasks Complete | In Progress | Ready to Start | Testing
176 | 40 | 2 | 24 | 0
Status | Task Count | Total Hours | % of Hours |  | Priority | Tasks | Hours
Ready to Start | 24 | 55 | 31.25% |  | High | 15 | 46
In Progress | 2 | 8 | 4.545% |  | Medium | 17 | 52
Testing in Progress | 0 | 0 | 0% |  | Low | 34 | 78
Complete | 40 | 113 | 64.2%
TOTAL | 66 | 176 | 100%
ℹ️ Hours use the Fibonacci scale (1,2,3,5,8,13,21,34,55,89). Duration on the Tracker sheet is auto-calculated: Finish − Start + 1.